BD STOCK OMS

Bangladesh Stock Exchange Order Management System

──────────────────────────────────────────────────────

PROJECT STATUS UPDATE

Current State  •  Revised Plan  •  Architecture Decisions

New Chat Start Prompt (copy-paste ready)

| Branch | Tests | Tables | Services | Status |
| --- | --- | --- | --- | --- |
| day-41-audit-compliance (complete) | 565 passing, 0 failing | 57 | 41 | Day 42 ready to start |

# 1. Where We Are Right Now

| Metric | Value | Notes |
| --- | --- | --- |
| Current Branch | day-41-audit-compliance | Pushed and complete |
| Test Count | 565 passing, 0 failing | Target was 555+ — exceeded |
| Database Tables | 57 | Two new tables added Day 40 (NotificationPreferences, NotificationLogs) |
| Services | 41 | Latest: IAuditComplianceService (Day 41) |
| Days Complete | 41 of 48 | 7 days remaining in original plan |
| Frontend | Not started | Begins Day 48 |
| Last Migration | Day40_NotificationEngine | Day 41 added no new tables |
| Seed Data | 15 stocks (DSE+CSE), default roles, sample users | In AppDbContext.OnModelCreating |
| Namespace | BdStockOMS.API (uppercase) | Critical — never change |
| Auth | JWT (memory) + httpOnly cookie refresh token | BCrypt work factor 11 |
| Redis | Token blacklist + session cache | Real-time SignalR alerts active |

## Completed Days Summary

| Day | Branch | Feature Built | Tests | New Tables |
| --- | --- | --- | --- | --- |
| 1–27 | (foundation) | Auth, Users, Stocks, Orders, RMS, Portfolio, Commission, Fund Requests, Market Data, Notifications, Watchlists, 2FA, KYC groundwork, CCD, Admin Dashboard, Audit Logging, Corporate Actions, News, Trader Reassignments, Order Amendments, System Settings | 281 | 45 |
| 28 | day-28-trading-dashboard | React 18 + TypeScript + Vite + Tailwind trading dashboard, JWT in memory, SignalR setup | 281 | 0 |
| 29 | day-29-exchange-connector | IExchangeConnector + SimulatedExchangeConnector + ExchangeConnectorFactory | 302 | 0 |
| 30 | day-30-order-state-machine | Trade model + OrderEvent model + IOrderStateMachine (state transitions) | 325 | 2 |
| 31 | day-31-trade-alerts | TradeAlert + RMS cash balance check + SignalR breach push | 342 | 1 |
| 32 | day-32-commission-ledger | CommissionLedger + ICommissionLedgerService + DSE fee breakdown | 357 | 1 |
| 33 | day-33-settlement | SettlementBatch + SettlementItem + T+2 engine | 374 | 2 |
| 34 | day-34-market-depth | MarketDepth + IMarketDepthService + 5-level order book | 390 | 1 |
| 35 | day-35-kyc | KycDocument + KycApproval + IKycService + full workflow | 416 | 2 |
| 36 | day-36-portfolio-analytics | PortfolioSnapshot + StockAnalytics + VWAP/52W/Beta/ROI | 440 | 2 |
| 37 | day-37-file-import | FileImportBatch + FileImportRow + CSV staging/validation/commit | 469 | 2 |
| 38 | day-38-brokerage-settings | BrokerageSettings + BranchOffice + feature toggles + trading hours | 494 | 2 |
| 39 | day-39-broker-summary | BrokerSummaryService + TraderMonitor + top-10 RBAC rankings | 516 | 0 |
| 40 | day-40-notification-engine | IEmailService + ISmsService (simulated) + NotificationDispatcherService | 540 | 2 |
| 41 | day-41-audit-compliance | AuditComplianceService + suspicious activity detection + CSV export | 565 | 0 |

# 2. New Architecture Decisions Made

Two major architectural decisions were made and approved after Day 41. These are implemented as a parallel track alongside the remaining plan — they do not replace any planned day.

## Decision 1: Per-Brokerage Separate Databases

APPROVED: Every brokerage gets its own SQL Server database instead of sharing one. This is the only architecture that satisfies BSEC regulatory requirements for data segregation between licensed brokerages.

### How It Works

- Master Database: BdStockOMS_Master — contains BrokerageHouses, BrokerageConnections (encrypted connection strings), Roles, SystemSettings, AuditLogs

- Tenant Databases: BdStockOMS_{BrokerageName} (e.g. BdStockOMS_AlphaSecurities) — contains all brokerage-scoped data

- Dynamic DbContext: Every HTTP request reads BrokerageHouseId from JWT, resolves the correct connection string via ITenantContext, creates TenantDbContext pointing to that DB

- SuperAdmin Panel: Can provision a new tenant DB, run migrations on it, activate/deactivate brokerage — all from UI

- No UI deletion: Deleting a tenant DB must be done manually by a DBA — too dangerous to expose in UI

| Aspect | Old (Shared DB) | New (Per-Tenant DB) |
| --- | --- | --- |
| Data isolation | BrokerageHouseId filter (one bug = breach) | Physically separate — impossible to cross-read |
| DB name | BdStockOMS (one) | BdStockOMS_AlphaSecurities, BdStockOMS_PrimeSec, etc. |
| Migrations | One migration for all | Run per-tenant from SuperAdmin panel |
| Backup | One backup covers all | Independent backup per brokerage |
| Performance | Shared — noisy neighbour risk | Isolated — one brokerage can't slow another |
| BSEC compliance | Questionable | Satisfies data segregation requirement |
| SuperAdmin access | Direct DB queries | Query master DB + can connect to any tenant DB |

## Decision 2: Flextrade BOS Compliance Checklist

APPROVED: A SuperAdmin dashboard endpoint that evaluates every brokerage against a 10-point Flextrade BOS compliance checklist. Runs automatically daily at midnight (IHostedService) and caches results in Redis. SuperAdmin can also trigger on-demand refresh.

| Check # | Compliance Point | How Verified |
| --- | --- | --- |
| 1 | BrokerageSettings configured | BrokerageSettings record exists and TradingStartTime is set |
| 2 | TREC number present | BrokerageHouse.TrecNumber is not null/empty |
| 3 | At least one active branch | BranchOffices count >= 1 where IsActive=true |
| 4 | Commission rates configured | BrokerageCommissionRates has at least one active rate |
| 5 | RMS limits set | RMSLimits record exists for the brokerage |
| 6 | At least one active trader | Users with Role=Trader, IsActive=true, count >= 1 |
| 7 | Flextrade BOS last import | FileImportBatches — last successful import within 24 hours |
| 8 | BO Account format valid | All investors have BO numbers matching ^1201\d{16}$ |
| 9 | KYC queue clear | No KycDocuments stuck in Pending status > 7 days |
| 10 | Settlement up to date | No SettlementBatches in Pending status older than T+3 |

# 3. Revised Complete Plan (Days 42–48)

The parallel track (per-brokerage DB + compliance checklist) is added to Day 42 alongside the original contract notes feature. All other days remain unchanged. Test targets are updated to reflect the additional work.

| Day | Branch Name | What Gets Built | Test Target | New Tables |
| --- | --- | --- | --- | --- |
| 42 | day-42-tenant-db-compliance | PARALLEL TRACK A: Per-brokerage database provisioning — BrokerageConnections model, ITenantDbContextFactory, TenantDbContext, dynamic connection resolution, SuperAdmin provisioning endpoints, migration runner per tenant PARALLEL TRACK B: Flextrade BOS compliance checklist — IFlextradeBosComplianceService, 10-point check, IHostedService daily scheduler, Redis cache, SuperAdmin dashboard endpoint ORIGINAL: Contract Notes + Report Engine — IReportService, trade PDF generation, daily trade ledger, monthly investor statement | 590+ | 2 (BrokerageConnections, ComplianceCheckResults) |
| 43 | day-43-flextrade-bos-xml | DSE Flextrade BOS XML Integration — Clients-UBR.xml + Positions-UBR.xml parser, MD5 ctrl file verification against Flextrade-BOS-Control.xsd, client reconciliation vs Users table, position reconciliation vs Portfolios table, RBAC upload dashboard, EOD position export to DSE-compatible XML | 620+ | 1 (BosImportSessions) |
| 44 | day-44-integration-concurrency | Integration Tests using WebApplicationFactory + real SQL Server, Concurrency Tests for simultaneous order placement race conditions, parallel RMS enforcement, deadlock detection | 660+ | 0 |
| 45 | day-45-performance-load | Redis TTL caching strategy (market data, commission rates, portfolio values), database index audit + missing indexes added, NBomber load test — 100 concurrent users, p95/p99 latency measurement | 680+ | 0 |
| 46 | day-46-vapt | VAPT Security Tests — OWASP ZAP automated scan, IDOR tests (user A accessing user B data), JWT tampering (alg:none, expired, modified signature), auth bypass attempts, BOLA tests, rate limiting implementation | 705+ | 0 |
| 47 | day-47-security-hardening | MFA mandatory for Admin/SuperAdmin roles, single active session enforcement (new login revokes all previous), UserPermissions fine-grained per-user endpoint overrides, session audit trail | 725+ | 1 (UserPermissions) |
| 48 | day-48-final-validation | All tests green, Swagger docs complete, Backend-Complete.md written, React frontend development begins — Dashboard, Login, Order Form, Portfolio View | 725+ | 0 |

### Updated Table Count Projection

| After Day | New Tables Added | Running Total |
| --- | --- | --- |
| 41 (current) | — | 57 |
| 42 | BrokerageConnections, ComplianceCheckResults | 59 |
| 43 | BosImportSessions | 60 |
| 44–46 | None | 60 |
| 47 | UserPermissions | 61 |
| 48 (final) | — | 61 |

# 4. Standing Rules (Never Change These)

| Rule | Value/Detail |
| --- | --- |
| Shell | Git Bash only — forward slashes always |
| Code language | Pure C# for all project code — Python only for file writing in bash terminal |
| File writing in bash | Use heredoc: cat > /tmp/script.py << 'PYEOF' ... PYEOF — avoids bash ! expansion bug |
| Namespace | BdStockOMS.API (uppercase API) — never lowercase |
| Test files location | BdStockOMS.Tests/Unit/ |
| Service interfaces location | BdStockOMS.API/Services/ (same folder as implementation) |
| Tests must increase every day | Every day adds new tests — never commit with fewer tests than previous day |
| Full code always | Never say 'refer to previous code' — always write complete files |
| End of day checklist | dotnet test → git commit → docs/Day-XX.md → git push |
| No localStorage | JWT in React memory only — refresh token in httpOnly Secure SameSite=Strict cookie |
| No frontend until Day 48 | All Days 1–47 are backend only |
| Guide style | 1 step at a time — wait for output before giving next step |
| Migrations | One migration per day — named Day{N}_{FeatureName} |
| Branch naming | day-{N}-{feature-slug} (e.g. day-42-tenant-db-compliance) |
| DI registration | All new services registered in Program.cs on the day they are built |
| RBAC | Every controller endpoint has explicit [Authorize(Roles=...)] — no open endpoints except login/register |

# 5. Copy-Paste Prompt for Next Chat

Copy everything in the grey box below and paste it as your first message in a new Claude chat. It contains the full project context, all decisions made, and the exact start command for Day 42.

━━━ START OF PROMPT — COPY FROM HERE ━━━

I am building BD Stock OMS (Bangladesh Stock Exchange Order Management System).

This is a demo project with plug-and-play exchange connector architecture.

GitHub: https://github.com/EshanBarua14/BdStockOMS

Current branch: day-41-audit-compliance (pushed and complete)

Tech Stack:

- Backend: ASP.NET Core 8, SQL Server, Redis, SignalR, EF Core 8

- Frontend: React 18 + TypeScript + Vite + Tailwind CSS (in BdStockOMS.Client/)

- Auth: JWT (memory only) + httpOnly cookie refresh token, BCrypt work factor 11

- Tests: xUnit + Moq — currently 565 passing, 0 failures

- Namespace: BdStockOMS.API (uppercase — critical)

- Test files: BdStockOMS.Tests/Unit/

- Service interfaces: BdStockOMS.API/Services/ (same folder as implementation)

- Python only for file writing in bash — all project code is pure C#

- File writing uses heredoc: cat > /tmp/x.py << 'PYEOF' to avoid bash ! expansion bug

COMPLETED DAYS:

Day 28: Trading Dashboard frontend | 281 tests

Day 29: IExchangeConnector + SimulatedExchangeConnector + ExchangeConnectorFactory | 302

Day 30: Trade + OrderEvent models + IOrderStateMachine | 325

Day 31: TradeAlert + RMS cash balance check + SignalR breach notifications | 342

Day 32: CommissionLedger + ICommissionLedgerService | 357

Day 33: SettlementBatch + T+2 engine | 374

Day 34: MarketDepth + IMarketDepthService + 5-level order book | 390

Day 35: KYC workflow — KycDocument, KycApproval, IKycService | 416

Day 36: PortfolioSnapshot + StockAnalytics + VWAP/52W/Beta/ROI | 440

Day 37: Back office file integration — CSV staging/validation/approval/commit | 469

Day 38: BrokerageSettings + BranchOffice + feature toggles + trading hours | 494

Day 39: BrokerSummaryService + TraderMonitor — top 10 rankings, RBAC | 516

Day 40: IEmailService + ISmsService (simulated) + NotificationDispatcherService | 540

Day 41: AuditComplianceService + suspicious activity detection + CSV export | 565

EXISTING TABLES (57 total):

Roles, BrokerageHouses, Users, Stocks, Orders, Portfolios, AuditLogs, SystemLogs,

RefreshTokens, LoginHistories, PasswordHistories, TwoFactorOtps, TrustedDevices,

UserSessions, CommissionRates, BrokerageCommissionRates, InvestorCommissionRates,

RMSLimits, SectorConfigs, CorporateActions, FundRequests, MarketData, NewsItems,

Watchlists, WatchlistItems, Notifications, SystemSettings, OrderAmendments,

TraderReassignments, Trades, OrderEvents, TradeAlerts, CommissionLedgers,

SettlementBatches, SettlementItems, MarketDepths, KycDocuments, KycApprovals,

PortfolioSnapshots, StockAnalytics, FileImportBatches, FileImportRows,

BrokerageSettings, BranchOffices, NotificationPreferences, NotificationLogs

EXISTING SERVICES (41 total):

IAuthService, IUserService, IStockService, IOrderService, ICCDService,

IAuditService, IPasswordService, ICommissionCalculatorService, IRMSValidationService,

IFundRequestService, INotificationService, IWatchlistService, IPortfolioPnlService,

IBrokerageReportService, ISystemSettingService, IAdminDashboardService,

IOrderAmendmentService, ITraderReassignmentService, IMarketDataService,

ICorporateActionService, INewsService, ITwoFactorService, ITokenBlacklistService,

ITenantContext, IExchangeConnectorFactory, IOrderStateMachine,

ICommissionLedgerService, ISettlementService, IMarketDepthService, IKycService,

IPortfolioSnapshotService, IFileImportService, IBrokerageSettingsService,

IBrokerSummaryService, IEmailService, ISmsService, INotificationDispatcherService,

IAuditComplianceService

ARCHITECTURE DECISIONS LOCKED IN:

1. PER-BROKERAGE SEPARATE DATABASES (approved):

- Master DB: BdStockOMS_Master (BrokerageHouses, BrokerageConnections, Roles,

SystemSettings, AuditLogs)

- Tenant DB naming: BdStockOMS_{BrokerageName} (spaces/special chars stripped)

e.g. BdStockOMS_AlphaSecurities

- Dynamic DbContext: reads BrokerageHouseId from JWT, resolves connection string

from BrokerageConnections table, creates TenantDbContext per request

- SuperAdmin can: provision new tenant DB, run migrations, activate/deactivate

- NO UI deletion: tenant DB deletion is DBA-only

2. FLEXTRADE BOS COMPLIANCE CHECKLIST (approved):

- IFlextradeBosComplianceService: 10-point checklist per brokerage

- Checks: BrokerageSettings, TREC number, active branch, commission rates,

RMS limits, active trader, last BOS import < 24h, BO account format,

KYC queue clear, settlement up to date

- Auto-runs daily at midnight via IHostedService, cached in Redis

- SuperAdmin can trigger on-demand refresh

- SuperAdmin-only endpoint

REMAINING PLAN:

Day 42: Tenant DB provisioning + BOS Compliance Checklist + Contract Notes | 590+

Day 43: DSE Flextrade BOS XML — Clients-UBR + Positions-UBR, MD5 ctrl | 620+

Day 44: Integration Tests + Concurrency Tests (WebApplicationFactory) | 660+

Day 45: Performance + Redis caching + NBomber load tests | 680+

Day 46: VAPT — OWASP ZAP, IDOR, JWT tampering, auth bypass | 705+

Day 47: Security Hardening — MFA for Admin/SuperAdmin, single session | 725+

Day 48: Final validation + Frontend begins | 725+

RULES (always apply):

- Git Bash only, forward slashes

- Full code always — never 'refer to previous'

- Tests must increase every day

- End each day: dotnet test + git commit + docs/Day-XX.md + git push

- No localStorage — memory + httpOnly cookies only

- No frontend work until Day 48

- Namespace is BdStockOMS.API (uppercase API)

- Guide me 1 step at a time, wait for output before next step

- Python only for file writing in bash — all project code is pure C#

- Use heredoc for file writing: cat > /tmp/x.py << 'PYEOF' ... PYEOF

DSE FLEXTRADE BOS FILE NOTE (Day 43):

Two XML file pairs uploaded every morning before trading:

- Clients-UBR.xml + Clients-UBR-ctrl.xml (MD5 hash control file)

- Positions-UBR.xml + Positions-UBR-ctrl.xml (MD5 hash control file)

ctrl files use Flextrade-BOS-Control.xsd schema. Day 43 builds:

XML parser, MD5 verification, client/position reconciliation,

RBAC dashboard, EOD export back to DSE-compatible XML.

START COMMAND — run this first:

cd /e/Projects/BdStockOMS

git checkout -b day-42-tenant-db-compliance

git status

dotnet test --no-build 2>&1 | tail -3

Paste the output and we will start Day 42 immediately.

━━━ END OF PROMPT — COPY UP TO HERE ━━━

# 6. Quick Reference Card

## Key File Locations

| What You Need | Where It Is |
| --- | --- |
| Add a new service interface + implementation | BdStockOMS.API/Services/IMyService.cs + MyService.cs |
| Register a new service | BdStockOMS.API/Program.cs — AddScoped<IMyService, MyService>() |
| Add a new database table | BdStockOMS.API/Models/MyModel.cs + add DbSet in AppDbContext.cs |
| Create a migration | cd BdStockOMS.API && dotnet ef migrations add Day42_FeatureName |
| Run migrations | cd BdStockOMS.API && dotnet ef database update |
| Add a new controller | BdStockOMS.API/Controllers/MyController.cs |
| Write tests | BdStockOMS.Tests/Unit/MyServiceTests.cs |
| Run all tests | cd /e/Projects/BdStockOMS && dotnet test |
| Run specific test | dotnet test --filter "MyTest_MethodName" |
| Write a file safely in bash | cat > /tmp/write.py << 'PYEOF' ... PYEOF && python /tmp/write.py |
| Day progress log | docs/Day-42.md |

## Common Errors & Fixes

| Error | Cause | Fix |
| --- | --- | --- |
| bash: !something: event not found | Bash ! expansion in double-quoted strings | Use heredoc: cat > /tmp/x.py << 'PYEOF' |
| CS0246: type not found in interface file | Missing 'using BdStockOMS.API.Models;' | Add using directive at top of interface file |
| CS0117: X does not contain Y | Wrong property name (e.g. Type vs OrderType) | grep -n 'property' Models/Order.cs to check |
| Build failed — 0 errors shown | Already inside BdStockOMS.API folder | Run: dotnet build (not dotnet build BdStockOMS.API) |
| Moq: 0 invocations performed | Service logic bug — branch not reached | Check if !prefs.Any() guard is present and correct |
| enum == string compile error | Role is a navigation property, not enum | Use u.Role.Name == roleString |
| InMemory enum filter returns empty | EF InMemory LINQ-to-SQL enum translation issue | Load to list first, then filter in-memory with .Where() |

## RBAC Quick Reference

| Role | Can Do |
| --- | --- |
| SuperAdmin | Everything — all brokerages, system settings, tenant DB provisioning, compliance checklist |
| Admin | Everything within their own brokerage — user management, order approval, reports |
| Compliance | Read-only: audit logs, suspicious activity, KYC queue, settlement monitoring, BOS compliance |
| Broker | Order placement, client management, fund requests within their brokerage |
| Trader | Order execution for assigned investors, portfolio view, order history |
| Investor | Own orders, own portfolio, own notifications, fund requests, watchlists |